## Sheet1
Phase | Task Name | Description | Estimated Days
A. System Setup & Environment | Camera Integration (Raspberry Pi) | Setup and configure Raspberry Pi camera for image and video capture. | 1
| Server Communication Setup | Develop Python communication between Raspberry Pi and Windows server for image/data transfer. | 1
| Database Configuration | Design and setup a local SQLite/MySQL schema for QC, OCR, and color detection data storage. | 1
B. Vision Processing Modules | QR Scanning Module | Implement QR code detection and decoding for model identification. | 1
| OCR Recognition Module | Develop OCR engine using Tesseract to read text from captured images. | 1
| Color Detection Module | Implement RGB-based color detection and comparison logic. | 1
| Image Quality & Blur Check | Add validation to reject or re-capture blurred or unclear images. | 0.5
C. QC Operations | Model Selection & Job Handling | Enable manual or QR-based model selection and job creation for inspection. | 1
| Capture & Evaluation Workflow | Implement image capture, OK/NOK marking, recapture, and result acknowledgment workflow. | 1
| Polygon & Shape Indicators | Show polygons, boxes, or rings to highlight OCR and color detection regions. | 1
| Zoom & Image Review Feature | Allow zooming and detailed inspection of each captured part or OCR region. | 1
D. Reporting & Data Management | QC Reporting & Dashboard | Create a reporting interface showing OK/NOK/Total counts with filters and pie chart. | 1
| Data Backup & Auto-Purging | Implement data backup and automatic purging of old image data. | 1
| CSV/Excel Export | Enable export of reports and QC data in CSV or Excel format. | 0.5
E. User & Admin Management | User Login & Password Verification | Add secure operator login with password-based local verification (no cloud users). | 0.5
| Master Data Management | Create CRUD (add/edit/delete) options for Models, OCR templates, and Color settings. | 0.5
F. Testing & Documentation | System Testing & Validation | Perform functional and integration testing for all modules. | 0.5
| User Manual & Final Documentation | Prepare a detailed operator manual and final documentation. | 0.5
16/11/2025